Acquisition and Selection of Projects Timeline: Plan for Neighbourhoods (PfN) DRAFT
## Key Milestones
- April - May 2025: We will review and adjust existing projects to ensure alignment with PfN criteria.
- June - July 2025: We will complete the rescoring and evaluation of projects, finalising our selection of priority projects.
- August - September 2025: We will finalise project selection, confirm pre-approval, and allocate funding.
- October - December 2025: We will prepare for project delivery; mobilise resources, hire staff, and initiate the first-phase projects.
- April 2026: We will begin project implementation with the release of funding.
1. Initial Review and Preparation (April - May 2025)
Goal: Thoroughly prepare for rescoring and realigning our existing projects with the updated PfN criteria, ensuring a solid foundation for a transparent and efficient project selection process.
Key Actions:
- Review Existing Projects: Examine all the projects submitted in the open call, ensuring clarity on their scope, impact, and alignment with PfN goals.
- Review PfN Criteria: We will familiarise ourselves with and refine the updated PfN scoring criteria to ensure they reflect both the community's needs and the programme's objectives.
- Communicate Changes to Stakeholders: We will actively inform all relevant stakeholders about changes in the funding structure and timeline, providing clear context on the adjustments made.
- Revisit Project Plans: Review and adjust our 10-year vision and 3-year plan if needed.
2. Rescoring and Evaluation (June - July 2025)
Goal: We will rigorously assess all existing projects based on the updated PfN criteria and select the highest-scored projects.
Key Actions:
- Rescore Existing Projects: We will rescore each project against PfN’s criteria—such as community impact, sustainability, alignment with PfN objectives, and risk—ensuring a fair and robust evaluation.
- Select Highest-Scored Projects: We will select the highest-scored projects based on the rescoring process, ensuring we prioritise those with the most potential for positive community impact.
- Develop a Rescore Report: We will document the process and rationale behind the rescoring and selection of the highest-scored projects, ensuring transparency throughout the process.
- Community Feedback: We will gather input from the community, ensuring that their priorities are fully reflected in the project selection process.
3. Final Selection and Approval (August - September 2025)
Goal: Finalise the project selection, the highest-scored projects based on the rescoring process, ensuring that all projects align with PfN’s strategic objectives. This step will set the stage for successful project delivery.
Key Actions:
- Submit Final Project Proposals: We will request and prepare detailed proposals for the highest-scored projects, including timelines, budgets, and anticipated impacts.
- Governance Review: We will ensure that strong governance structures are in place to oversee the delivery of each project, ensuring compliance with PfN’s requirements and community expectations.
- Pre-Approval Confirmation: Projects will be considered pre-approved if they align with the PfN interventions. We will verify that the highest-scored projects comply with these criteria, ensuring they are eligible and ready for funding.
- Allocate Funding: We will ensure that both capital and revenue funding are allocated to the approved projects, ensuring resources are available for timely implementation.
4. Project Initiation and Kick-off (October - December 2025)
Goal: Prepare for the official start of project delivery, ensuring that all resources are in place and the right partnerships are established.
Key Actions:
- Mobilise Resources: We will finalise recruitment, contracts, and materials required for the smooth initiation of projects.
- Project Initiation: We will officially launch selected projects, ensuring that all stakeholders are aligned with the vision, goals, and timelines.
- Stakeholder Engagement: We will continue to build and nurture relationships with all stakeholders, ensuring open lines of communication throughout the project delivery phase.
- Monitoring and Reporting Mechanism: Establish systems for monitoring project progress and outcomes, ensuring alignment with the PfN’s monitoring and evaluation strategy.
5. Programme Delivery (Start) (April 2026)
Goal: The delivery phase will begin with the release of funding and the official commencement of projects.
Key Actions:
- Funding Release: Central government will release the programme delivery funding to local authorities to support project implementation.
- Project Implementation: We will begin on-the-ground work for the delivery of approved projects as per the established plans.
- Monitoring and Adjustments: We will continuously assess project progress and make necessary adjustments to ensure that each project is successfully delivered.